## Report
Atlas review · décisions et impacts
Atlas customer portal | 2026-10-15T15:18:27.132Z | Fictional example data
Project | Section | Record | Field | Content | Sources
Atlas customer portal | Executive summary | Atlas customer portal | Selected records | 2 decisions · 3 changes · 2 stories | 2709e3d6-b9df-4970-9f0a-fb6f872745db
Atlas customer portal | Executive summary | Atlas customer portal | Audience | Project leadership | 2709e3d6-b9df-4970-9f0a-fb6f872745db
Atlas customer portal | Executive summary | Atlas customer portal | Introduction | A traceable review of the fictional Atlas project. | 2709e3d6-b9df-4970-9f0a-fb6f872745db
Atlas customer portal | Executive summary | Atlas customer portal | Reference period | All dates / All dates | 2709e3d6-b9df-4970-9f0a-fb6f872745db
Atlas customer portal | Executive summary | Atlas customer portal | Data status | Fictional example data | 2709e3d6-b9df-4970-9f0a-fb6f872745db
Atlas customer portal | Decisions | Make data exports self-service | Status | accepted | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Owner | Alex Morgan (fictional) | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Decision date | 10/15/2026 | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Context & problem | Support currently prepares account exports manually. Customers need a repeatable way to retrieve their own records. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Selected solution | Offer CSV export from the account workspace. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Rationale | A focused self-service flow addresses a recurring request without introducing a reporting platform. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Alternatives | Keep support-assisted exports Advantages: No implementation effort. Trade-offs: Continued wait time and support effort. Add self-service CSV export Advantages: Customers can retrieve records directly. Trade-offs: Requires access-control and failure handling. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Assumptions | The existing account model defines the accessible record scope. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Constraints | No changes to the authorization model in this release. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Make data exports self-service | Stakeholders | Product, Engineering, Customer support | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Status | proposed | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Owner | Alex Morgan (fictional) | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Decision date | 10/15/2026 | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Context & problem | Support currently prepares account exports manually. Customers need a repeatable way to retrieve their own records. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Selected solution | Not recorded | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Rationale | Validate the main workflow before expanding the release scope. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Assumptions | The existing account model defines the accessible record scope. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Constraints | No changes to the authorization model in this release. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Decisions | Keep the first release focused on desktop workflows | Stakeholders | Product, Engineering, Customer support | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Scope & changes | Baseline v1 | Objective | Give customers a reliable account workspace with clear access to their own records. | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Status | Frozen | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Calculation context | Snapshot includes every accepted change for this baseline through the reference end date. Selection and start date filter the register, not the snapshot. | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Initial effort · estimate | 16 person-days | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Current effort · estimate | 20 person-days | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Effort change · estimate | 4 person-days | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Current deliverables | Account overview: 5 person-days (must) Activity timeline: 8 person-days (must) Workspace settings: 3 person-days (should) Self-service CSV export: 4 person-days (must) | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Assumptions | Estimates are fictional planning inputs, not delivery commitments. | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Constraints | One release; existing account service. | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Baseline v1 | Attention points | Recorded risk — Self-service CSV export: Confirm the maximum supported export size. | a9d97d14-f048-449d-96ad-aff429de93f2; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Scope & changes | Self-service CSV export | Status | accepted | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Self-service CSV export | Change type | addition | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Self-service CSV export | Description | Add an export action for customer account records. | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Self-service CSV export | Justification | Implements the self-service export decision. | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Self-service CSV export | Requested by | Sam Chen (fictional) | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Self-service CSV export | Effort input | 4 person-days (input) | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Self-service CSV export | Dependencies | Account overview | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Status | proposed | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Change type | addition | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Description | Let customers save their export column selection. | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Justification | Potential follow-up for repeat exports. | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Requested by | Sam Chen (fictional) | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Effort input | 3 person-days (input) | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Saved export presets | Dependencies | Account overview | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Status | rejected | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Change type | addition | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Description | Add a configurable reporting dashboard. | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Justification | Outside the focused first release. | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Requested by | Sam Chen (fictional) | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Effort input | 13 person-days (input) | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Scope & changes | Custom reporting dashboard | Dependencies | Account overview | 8ca5d728-3696-4827-b97d-1c6eb23a8b5f; a9d97d14-f048-449d-96ad-aff429de93f2
Atlas customer portal | Story refinement | Export account records | Original story | As an account administrator, I want to export my account records easily, so that I can prepare internal reports. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | User story | As an account administrator, I want to export my account records easily, so that I can prepare internal reports. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | User / persona | Account administrator | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | Need | Export the records available in my account workspace. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | User value | Prepare internal reporting without waiting for support. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | Acceptance criteria | Given an authenticated account administrator with accessible records, when they request a CSV export, then a CSV file containing those records is downloaded. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | Open questions | “easily” is subjective and does not define an observable threshold. What observable condition would demonstrate “easily”? Agree on a measurable expectation. No error condition is mentioned in the story or criteria. Which failure conditions are relevant here, and what feedback should the user receive? The empty-data case is not described. What should happen when there are no data to export? | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | Business rules | Apply the existing account access permissions. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | Constraints | CSV only for the first release. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Export account records | Dependencies | Account overview and existing authorization rules. | d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Story refinement | Understand the activity timeline | Original story | As an account administrator, I want a fast and intuitive activity timeline. | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Story refinement | Understand the activity timeline | User story | As an account administrator, I want a fast and intuitive activity timeline. | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Story refinement | Understand the activity timeline | User / persona | Account administrator | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Story refinement | Understand the activity timeline | Need | See account activity in chronological order. | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Story refinement | Understand the activity timeline | User value | Understand recent updates. | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Story refinement | Understand the activity timeline | Open questions | “fast” is subjective and does not define an observable threshold. What observable condition would demonstrate “fast”? Agree on a measurable expectation. “intuitive” is subjective and does not define an observable threshold. What observable condition would demonstrate “intuitive”? Agree on a measurable expectation. No acceptance criteria are recorded. Given [confirmed context], when [the requested action occurs], then [an observable result]. Replace each placeholder with an agreed fact. No error condition is mentioned in the story or criteria. Which failure conditions are relevant here, and what feedback should the user receive? No business rules are recorded. They may be unnecessary; confirm with the team. Are there eligibility, permission, or data-handling rules to confirm? | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Story refinement | Understand the activity timeline | Dependencies | Account overview | e6d12a12-320e-4f8f-9cbf-b79fb0dfc2ef
Atlas customer portal | Recorded connections | Make data exports self-service → Self-service CSV export | Relationship | informs | 972cd581-c94a-4e2c-aea4-8d04d1b47515; 738b066a-a2c2-4b26-a44e-6eed637dd041; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Recorded connections | Make data exports self-service → Self-service CSV export | Relationship context | The decision provides the rationale for this scope addition. | 972cd581-c94a-4e2c-aea4-8d04d1b47515; 738b066a-a2c2-4b26-a44e-6eed637dd041; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Recorded connections | Self-service CSV export → Export account records | Relationship | affects | 4929ae7b-a719-4250-9325-7f89b6193c9e; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Recorded connections | Self-service CSV export → Export account records | Relationship context | The story describes the export behavior introduced by this change. | 4929ae7b-a719-4250-9325-7f89b6193c9e; 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c; d149221e-de7d-4a9f-9ea1-6b08873731b0
Atlas customer portal | Attention points | Make data exports self-service | Attention points | Recorded assumptions have not been verified. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Attention points | Make data exports self-service | Attention points | Large exports may require a later asynchronous workflow. | 738b066a-a2c2-4b26-a44e-6eed637dd041
Atlas customer portal | Attention points | Keep the first release focused on desktop workflows | Attention points | Recorded assumptions have not been verified. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Attention points | Keep the first release focused on desktop workflows | Attention points | Large exports may require a later asynchronous workflow. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Attention points | Self-service CSV export | Known risks | Confirm the maximum supported export size. | 457abfc4-6b5d-4fb7-8fa8-9fe59830a11c
Atlas customer portal | Arbitrations & next actions | Keep the first release focused on desktop workflows | Arbitration required | Review the proposed decision with the recorded owner. | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Arbitrations & next actions | Keep the first release focused on desktop workflows | Owner | Alex Morgan (fictional) | 39be1c40-2325-4913-b3d6-df76cd762673
Atlas customer portal | Arbitrations & next actions | Saved export presets | Arbitration required | Accept or reject this proposal explicitly after reviewing its impacts. | 3da8f527-d53b-4dc7-8fca-ca56bd6f6283